Abstract from TI NOSC Technical Report
Full Technical Report is Available from the DoD Ada Software Repository
  on SIMTEL20
Prepared by Richard Conn, TI Ada Technology Branch, 26 Sep 85


                               CHAPTER 3

                   SOFTWARE PRODUCTIVITY INFORMATION



           In this chapter, Texas Instruments reports on  Software  life
      cycle  labor  distribution  (as gathered from our labor collection
      system), productivity (LOC) and experiences with software reuse.


		< Detail Omitted >


      3.2  SOFTWARE LIFE CYCLE LABOR DISTRIBUTION

           In order that proper  tracking  of  project  hours  could  be
      accomplished, we established labor categories reflective of the SW
      life cycle within our labor reporting system.   As  the  engineers
      advanced  thru  the  life  cycle,  time  was charged to the charge
      number corresponding to the phase.  Analysis of the data indicates
      hours  were  spent  as  follows.  Several numbers in this data may
      appear suspect; this is how the  labor  system  recorded  it;  the
      accuracy  of  this data is subject to the normal problem of humans
      inputting the correct data.


                          Virtual  | Spelling  |   Style  |  Batch/Forms
                          Terminal | Corrector |  Checker |   Generator
                          ======== | ========= |  ======= |  ===========
      Requirements                 |           |          |
      System Spec                  |   11   1% |          |
      Preliminary Design           |  458  30% | 416  28% |   397  29%
      Users manual         16   1% |  100   7% |  35   2% |    35   3%
      Detailed design     344  20% |   40   3% | 148  10% |   223  16%
      Implementation      634  37% |  604  40% | 517  35% |   559  40%
      Training              8   0% |    8   1% |  12   1% |     8   1%
      Integration                  |           |          |     4   0%
      Qaulity Assurance    26   2% |           |          |
      Testing             594  35% |  226  15% | 273  18% |    79   6%
      Data management       4   0% |           |          |
      Configuration Mgt     1   0% |    3   0% |   3   0% |     1   0%
      ------------------           |           |          |
      Sub Total          1627      | 1450      |1404      |  1306
      Program Management   76   4% |   76   5% |  75   5% |    75   5%
      ------------------           |           |          |
      Grand Total        1703      | 1526      |1479      |  1381
      Manmonths          9.84      | 8.82      |8.58      |  7.98

	* Note: Percentages do not total to 100% due to roundoff errors


           While a manmonth is contractually approximated at 173  hours,
      many hours in excess of an 8 hour day were worked.

           Since this program was managed as  1  contract  with  4  task
      elements, program management time was accumulated as an aggregate;
      the hours spent are allocatable to the whole program, not any  one
      tool  in  particular.  Total program management hours was 303.  In
      the above table, these hours were allocated  equally  across  each
      tool.

           Requirements and  System  specification  had  little  charges
      because  the  proposals  written for these tools were written with
      the intent that they serve as the requirements and  specifications
      documents

           Configuration management  is  low  because  some  of  the  CM
      function  was  handled  by  a support group (not allocated to this
      project) and some was accomplished after the  data  was  extracted
      for  this  report.   In  any case, all Software and documents have
      been CM'd and a retrievable according to standard TI procedures.

      3.3  PRODUCTIVITY (LOC)

           TI used the PAGER tool from the Ada repository as  a  vehicle
      by which to count Ada statements, comments and total text lines in
      the tools.  This tool considers an Ada statement to be  terminated
      by a semicolon.  As such, a text line can contain one Ada comment,
      one or more Ada statements, or one or more Ada statements  and  an
      Ada comment.

           Following is a table indicating  the  lines  of  Ada  source,
      comments,  text  lines  and  testing  code  in  each  of the tools
      written.  Note that in the batch/form generator  and  the  virtual
      terminal,  testing  code had to be written to exercise the various
      interfaces; this code was also written in Ada.


                    Virtual     Spelling       Style         Batch/Forms
                    Terminal    Corrector     Checker         Generator
                    ========    =========     =======        ===========

      Ada Source:     2421        2743          3189          2869
      Comments:        590        2626          2013          1707
      Text Lines:     6300        9458          9762          8307

      Test Source     1218                                     163
      Comments:        155                                     200
      Text Lines:     1762                                    1398
      ---------
      Totals:
        Ada Source:   3639        2743          3189          3032
        Comments:      745        2626          2013          1907
        Text Lines:   8062        9458          9762          9705


           Any figures regarding lines of code/day must consider the way
      lines  of  code is determined.  Some techiques consider every text
      line in a program to be a line  for  measurement  purpose,  others
      only  count  executable  statements  and exclude comments and data
      definition.  Since there seems to be no universal agreement on the
      proper technique, for the purposes of this report, we will compute
      LOC based on both the total number of text  lines  and  the  total
      number  of Ada source statements.  In all cases, testing code will
      be counted.



                    Virtual     Spelling       Style         Batch/Forms
                    Terminal    Corrector     Checker         Generator
                    ========    =========     =======        ===========

      Ada Source:     3639        2743          3189          3032
      manmonths        9.84        8.82          8.55          7.98
      LOC/mm         369.8       311.0         372.98        379.9
      LOC/day         17.2        14.46         17.34         17.67

      Text Lines:     8062        9458          9762          9705
      manmonths        9.84        8.82          8.55          7.98
      LOC/mm         819.3      1072.3        1141.75       1216.16
      LOC/day         38.13       49.87         53.10         56.56



           LOC/day assumes 21.5 work days per month.  It should be noted
      that  these  tools did require some Mil-Std documentation, such as
      design specs, test plans/procedures, users manuals.  Where nothing
      was mandated in the CDRL list, internal TI documentation standards
      were used.





Output Data from the Manpower Projection Tool, a NOSC Tool created by
GTE West

The following charts and tables show projected manpower staffing based
on the Cocomo model in Semidetached mode.  The data is based on the Line
of Code count from each of the four NOSC tools.  Compare the projected
staffing with the actual staffing which was required.  Only the nominal
schedule is shown.




1. MANPOWER Projection Report for Virtual Terminal

                   Boehm / DeMarco / Estimated Staffing Profiles



   Lines of source code in thousands (KSLOC) =     8.0620

   Man-months of effort
    (equation from Barry W. Boehm, pg.75, table 6-1) =    31.0697

   Most likely delivery time
    (equation from Barry W. Boehm, pg.75, table 601) =     8.3226

   The impossible region
    (equation from Tom DeMarco, pg.181) =   5.973 months or less

   Equation mode type used: SEMIDETACHED

                         Nominal     Schedule
                         --------------------


 **********     Acceleration rate =   0.033
 *****   Peak staffing occurs around month   3.9     **********


 Staffing Estimate:                                         Month      Est. Staff
                                                            -----     ----------
      5 |  **                                                 1         1.98404
      4 | *  **                                               2         3.59405
      3 |      *                                              3         4.57106
      2 |*      *                                             4         4.83764
      1 |                                                     5         4.49323
        +--------                                             6         3.75051
        0  3  6                                               7         2.84921
                   Duration (months)                          8         1.98491



2. MANPOWER Projection for Spelling Corrector

                   Boehm / DeMarco / Estimated Staffing Profiles



   Lines of source code in thousands (KSLOC) =     9.4580

   Man-months of effort
    (equation from Barry W. Boehm, pg.75, table 6-1) =    37.1549

   Most likely delivery time
    (equation from Barry W. Boehm, pg.75, table 601) =     8.8602

   The impossible region
    (equation from Tom DeMarco, pg.181) =   6.340 months or less

   Equation mode type used: SEMIDETACHED

                         Nominal     Schedule
                         --------------------


 **********     Acceleration rate =   0.028
 *****   Peak staffing occurs around month   4.2     **********


 Staffing Estimate:                                         Month      Est. Staff
                                                            -----     ----------
      5 |  ****                                               1         2.02323
      4 | *    *                                              2         3.72043
      3 |       *                                             3         4.85158
      2 |*       *                                            4         5.31742
      1 |                                                     5         5.16617
        +---------                                            6         4.55603
        0  3  6  9                                            7         3.69361
                   Duration (months)                          8         2.77357
                                                              9         1.93851


3. MANPOWER Projection for Style Checker

                   Boehm / DeMarco / Estimated Staffing Profiles



   Lines of source code in thousands (KSLOC) =     9.7620

   Man-months of effort
    (equation from Barry W. Boehm, pg.75, table 6-1) =    38.4950

   Most likely delivery time
    (equation from Barry W. Boehm, pg.75, table 601) =     8.9708

   The impossible region
    (equation from Tom DeMarco, pg.181) =   6.415 months or less

   Equation mode type used: SEMIDETACHED

                         Nominal     Schedule
                         --------------------


 **********     Acceleration rate =   0.029
 *****   Peak staffing occurs around month   4.2     **********


 Staffing Estimate:                                         Month      Est. Staff
                                                            -----     ----------
      6 |   *                                                 1         2.16889
      5 |  * **                                               2         3.97635
      4 | *    *                                              3         5.15945
      3 |       *                                             4         5.61539
      2 |*       *                                            5         5.40679
      1 |                                                     6         4.71607
        +---------                                            7         3.77397
        0  3  6  9                                            8         2.79172
                   Duration (months)                          9         1.91830



4. MANPOWER Projection for Batch/Forms Generator

                   Boehm / DeMarco / Estimated Staffing Profiles



   Lines of source code in thousands (KSLOC) =     9.7050

   Man-months of effort
    (equation from Barry W. Boehm, pg.75, table 6-1) =    38.2434

   Most likely delivery time
    (equation from Barry W. Boehm, pg.75, table 601) =     8.9502

   The impossible region
    (equation from Tom DeMarco, pg.181) =   6.401 months or less

   Equation mode type used: SEMIDETACHED

                         Nominal     Schedule
                         --------------------


 **********     Acceleration rate =   0.028
 *****   Peak staffing occurs around month   4.2     **********


 Staffing Estimate:                                         Month      Est. Staff
                                                            -----     ----------
      5 |  ****                                               1         2.08250
      4 | *    *                                              2         3.82942
      3 |       *                                             3         4.99371
      2 |*       *                                            4         5.47319
      1 |                                                     5         5.31751
        +---------                                            6         4.68950
        0  3  6  9                                            7         3.80181
                   Duration (months)                          8         2.85482
                                                              9         1.99529